## Overview
🗺️ Offmap — Production Rollout Plan
Generated 2026-07-26 · Next.js · Supabase · Stripe · Vercel (EU / Frankfurt) · Colour-coded phase tracker
22 | ~$60 | 7 | ~Few days | 65/65
Phase 0 tasks | /mo at launch | phases / tabs | to go live | pages build ✓
KEY FACTS
Current status | Live on Vercel in MOCK/demo mode. Public pages work; auth flows require going to real mode (Supabase). Build green.
Live URL | offmap-iota.vercel.app (demo). Custom domain not purchased yet.
Critical blocker | Mock mode can't persist sessions on Vercel serverless — enable real Supabase for signup/login/messaging.
How to use | One tab per phase + Costs, Security & Risks. Filter/sort within tabs. Update the Status column as you go.
Priority legend | P0 = before go-live · P1 = before real users / soon · P2 = scale phase
Status legend | To do (amber) · In progress (blue) · Done (green)

## Phase 0 – Go Live
🚀 Phase 0 — Go Live (Make it Real)
The critical path to accept real users, subscriptions and payments. Do the red P0 items first.
# | Area | Task | Owner | Effort | One-off Cost | Priority | Status | Notes / How
1 | Database | Confirm Supabase prod project (Frankfurt eu-central-1) | You | 0.5h | €0 | P0 | To do | Project id fgaxgqexxyvvaocqseev
2 | Database | Apply Drizzle migrations 0000–0002 to prod | You+Claude | 1h | €0 | P0 | To do | Via GitHub migrate workflow or Supabase SQL editor (local port blocked)
3 | Database | Verify auth trigger + seed cities | You+Claude | 0.5h | €0 | P0 | To do | npx tsx drizzle/seed.ts
4 | Config | Set all prod env vars in Vercel; MOCK_MODE=false | You | 1h | €0 | P0 | To do | Supabase, Stripe, Upstash, Resend, CRON_SECRET, ANTHROPIC
5 | Config | Set NEXT_PUBLIC_APP_URL to prod domain | You | 5m | €0 | P0 | To do | Required for CSRF origin check
6 | Payments | Create 4 Stripe products (Day/Week/Month/Annual) | You | 0.5h | €0 | P0 | To do | Live mode; copy 4 price IDs
7 | Payments | Configure Stripe webhook → /api/webhooks/stripe | You | 0.5h | €0 | P0 | To do | 5 events; copy whsec_ signing secret
8 | Payments | Test subscription end-to-end (test card 4242…) | You+Claude | 0.5h | €0 | P0 | To do | Verify webhook fires + sub appears
9 | Cache | Create Upstash Redis DB (Frankfurt) + REST keys | You | 0.5h | ~$10/mo | P1 | To do | Rate limiting + cache
10 | Email | Resend API key + verify sending domain (DNS) | You | 1h | €0 | P1 | To do | 17 templates already wired
11 | Monitoring | Add Sentry (@sentry/nextjs) + DSN | Claude+You | 1h | €0 | P1 | To do | Error visibility BEFORE real users
12 | Monitoring | Enable Vercel Web Analytics | You | 5m | €0 | P1 | To do | Already consent-gated in code
13 | Security | Enable Supabase email verification | You | 15m | €0 | P0 | To do | Auth settings in dashboard
14 | Security | Verify RLS on all 14 tables with real auth | You+Claude | 1h | €0 | P0 | To do | Confirm cross-user isolation
15 | Security | Enable Dependabot + npm audit in CI | Claude | 0.5h | €0 | P1 | To do | Config already added
16 | Security | Enable Supabase PITR (backups) | You | 15m | incl. Pro | P1 | To do | Disaster recovery
17 | Domain | Buy domain (offmap.* — .com/.de/.eu) | You | 0.5h | ~€15/yr | P0 | To do | Not purchased; check trademark first
18 | Domain | Point DNS to Vercel + verify SSL | You | 0.5h | €0 | P0 | To do | Update NEXT_PUBLIC_APP_URL after
19 | QA | Smoke test: register→subscribe→message→host onboarding | You+Claude | 2h | €0 | P0 | To do | Money-path flows; no automated tests exist
20 | Deploy | Commit & push all pending work; prod deploy | Claude+You | 0.5h | €0 | P0 | In progress | This session's work is unpushed
21 | Legal | Fill real Impressum / Privacy / Terms details | You | 1h | €0 | P0 | To do | German § 5 TMG requires real details
22 | Compliance | Run Mozilla Observatory scan; fix findings | You+Claude | 0.5h | €0 | P1 | To do | Headers already in next.config.js

## Phase 1 – Launch
📣 Phase 1 — Launch & Monitor (0 → 500 users)
Once real users can sign up: monitoring, first hosts, marketing, on-platform bookings.
# | Area | Task | Owner | Effort | Cost | Priority | Status | Notes
1 | Monitoring | Betterstack uptime monitors + status page | You | 1h | ~$20/mo | P1 | To do | Monitor /, /search, login, /api/stats
2 | Supply | Manually vet & onboard first ~50 hosts | You | ongoing | €0 | P0 | To do | No auto ID verification yet
3 | Marketing | LinkedIn build-in-public (founder story) | You | ongoing | €0 | P0 | To do | See docs/GO_TO_MARKET.md
4 | Marketing | Instagram travel content + reels | You | ongoing | €0 | P1 | To do | Visual vertical = strong fit
5 | Marketing | Waitlist capture → convert to first users | You+Claude | 2h | €0 | P1 | To do | Turn audience into signups
6 | Revenue | On-platform bookings + Stripe Connect Express | Claude+You | 1–2wk | per-txn | P1 | To do | 15% host + 5% traveler; needs Connect wiring
7 | Legal | Register company (Kleingewerbe → UG) | You | varies | ~€300–1000 | P1 | To do | Entity for revenue/investment
8 | Ops | Enable Vercel cron for /api/cron/emails | You | 5m | incl. Pro | P1 | To do | Hourly reminders/digests
9 | Trust | Verified-host badge (one-time €15–25) | Claude+You | 3–5d | €0 | P2 | To do | Build at 50+ hosts

## Phase 2 – Scale
📈 Phase 2 — Scale (500 → 50k+ users)
Triggered by growth milestones — do NOT build ahead of the trigger.
# | Area | Task | Trigger | Effort | Cost | Notes
1 | DB | Review pooling / read replicas | 1k users | 1–2d | incl. | Supabase PgBouncer; reads → replica
2 | Observability | Grafana Cloud unified dashboard | 5k users | 2d | ~$50/mo | Vercel+Supabase+Upstash+Stripe
3 | Search | Host search → Typesense / Postgres FTS | 10k hosts | 1wk | ~$30/mo | LIKE queries won't scale
4 | Revenue | Host Featured/Pro tiers (€25–49/mo) | 20+ hosts/city | 1wk | per-sub | Analytics dashboard first
5 | Revenue | Traveler credit packs | one-time visitors | 1wk | per-txn | Alt to subscription
6 | Infra | Evaluate dedicated infra vs Vercel | 50k users | eval | varies | Only if costs justify
7 | Product | PWA / native app | post seed | weeks | varies | Phase 0 is web-only

## Hiring Plan
👥 Hiring Plan — Building the Team After Funding
Who to hire after the seed round, by stage. 1st hire de-risks the solo-founder bottleneck; then balance supply (hosts) & demand (marketing). Salaries = est. gross €/yr, German market.
Role | Stage | Priority | Seniority | Key Responsibilities | Est. Salary (€/yr, DE) | Type
Founding / Senior Full-Stack Engineer | Post-Seed | P0 | Senior | Own & scale the codebase, ship features, remove founder as single point of failure | €70–95k + equity | Full-time
Growth / Marketing Lead | Post-Seed | P0 | Mid-Sr | Demand generation (paid + organic), funnel, CAC/LTV, both marketplace sides | €60–85k | Full-time
Community / Host Success Manager | Post-Seed | P0 | Mid | Recruit, vet & onboard hosts; grow & retain supply; host relationships | €45–60k | Full-time
Product Designer | Post-Seed | P1 | Mid-Sr | UX/UI, design system, conversion optimisation (can start as contract) | €55–75k | Contract→FT
Customer Support / Trust & Safety | Post-Seed | P1 | Jr-Mid | User support, disputes, safety flags — critical for in-person meetups | €35–50k | FT / PT
Backend Engineer | Scale | P1 | Mid-Sr | Payments, bookings, Stripe Connect, infra scaling | €65–85k | Full-time
Frontend / Mobile Engineer | Scale | P1 | Mid | Web + PWA / native app | €60–85k | Full-time
Data / Analytics | Scale | P1 | Mid | Metrics, retention/cohorts, host ranking, marketplace liquidity | €55–70k | Full-time
Performance Marketer | Scale | P1 | Mid | Paid acquisition, SEO, channel scaling | €55–75k | Full-time
Trust & Safety / Ops Lead | Scale | P2 | Mid-Sr | KYC / ID verification, policy, moderation, incident response | €55–75k | Full-time
Finance / Operations Manager | Scale | P2 | Mid | Bookkeeping, payouts, compliance, investor reporting | €55–75k | FT / fractional
Head of Growth | Growth | P2 | Senior | Own growth org, multi-channel acquisition + retention | €90–130k | Full-time
City / Country Expansion Manager | Growth | P2 | Mid | Launch new cities; local supply/demand playbook | €45–65k | FT per market
Engineering Manager / CTO | Growth | P2 | Exec | Lead eng team, architecture, hiring | €100–150k + equity | Full-time
Senior Platform Engineers (×2–3) | Growth | P2 | Senior | Scale platform, search, reliability | €70–95k each | Full-time

## Costs
💶 Cost Breakdown
Estimates. Monthly recurring + one-time + variable. Currency as noted.
MONTHLY RECURRING (infrastructure)
Service | Plan | Monthly | When needed | Purpose
Vercel | Pro | $20 | Go-live | Hosting, serverless, ISR, cron, analytics
Supabase | Pro (Frankfurt) | $25 | Go-live | Postgres, Auth, Storage, PITR
Upstash Redis | Pay-as-you-go | ~$10 | Go-live | Rate limiting + cache
Resend | Free → Paid | $0 → $20 | Go-live | Email (free ≤3k/mo)
Sentry | Free | $0 | Go-live | Error monitoring (≤5k/mo)
Anthropic (Alma) | Pay-as-you-go | ~$5 | Optional | AI concierge (Haiku)
Betterstack | Starter | ~$20 | Phase 1 | Uptime + status page
Subtotal at go-live |  | ~$60/mo
Subtotal w/ monitoring (Phase 1) |  | ~$80–100/mo
ONE-TIME / ANNUAL
Item | Cost
Domain (offmap.*) | ~€15 / yr
EU/DE Trademark (optional) | ~€850–1000
Company registration (UG) | ~€300–1000
VARIABLE (per transaction)
Item | Fee
Stripe — European cards | 1.5% + €0.25 / txn
Stripe Connect payout | +0.25% + €0.25

## Security & GDPR
🔒 Security & GDPR Checklist
Germany / EU — non-negotiable items before and at go-live.
# | Item | Category | Priority | Status | Notes
1 | RLS enabled on all 14 tables | Access | P0 | Done | Re-verify with real auth
2 | No PII in server logs | Privacy | P0 | Done | Audited 2026-06
3 | Sanitised error responses | Privacy | P0 | Done
4 | GDPR data export endpoint | Rights | P0 | Done | /api/me/data-export
5 | Account deletion / anonymisation | Rights | P0 | Done | 30-day; keep financial 10y
6 | CSRF origin check (middleware) | Web | P0 | Done | Needs NEXT_PUBLIC_APP_URL
7 | Security headers (CSP/HSTS/XFO) | Web | P0 | Done | Run Observatory
8 | Cookie consent (TTDSG) | Privacy | P0 | Done | Built this session
9 | Email verification enforced | Auth | P0 | To do | Supabase setting
10 | Leaked-password protection | Auth | P1 | To do | Supabase setting
11 | Stricter auth rate limiting | Auth | P1 | To do | 5/15min
12 | Bookings RLS | Access | P1 | To do | When bookings live
13 | Sentry error monitoring | Ops | P1 | To do | Before real users
14 | Data stored in EU (Frankfurt) | GDPR | P0 | Done | eu-central-1
15 | IP hashing after 7 days | GDPR | P1 | To do | Confirm job
16 | Breach notification runbook (72h) | GDPR | P1 | To do | BfDI Berlin

## Risks
⚠️ Key Risks & Mitigations
Known risks going into production.
Risk | Impact | Likelihood | Mitigation
Mock mode can't do auth on Vercel | High | Certain | Go to real mode (Supabase) — Phase 0 resolves it
Local network blocks Postgres port | Med | Certain | Run migrations via CI/Vercel, not laptop
Bad DB migration in prod | High | Low | PITR + nullable-first / backwards-compatible rules
Stripe outage | Med | Low | Existing subs work from DB; queue new & retry
Redis outage | Low | Low | Fail open → DB fallback (coded)
No automated tests | Med | Certain | Manual smoke-test checklist of money paths
Unverified hosts (no auto KYC) | Med | Med | Manual vetting first 50; Stripe Identity later
Founder bandwidth (solo) | High | High | Managed services; P0 only; defer P2